## Acquisition Plan
Acquisition Process Timeline
Task | Duration | Assigned to: | Task ID | Note: This timeline approximates the milestones for the acquisition plan. The duration of each step may vary for and should be used for informational purposes only.
Develop Acquisition Package | 1 day | Person assigned to | Task #
Statement of Need | 1 day | Person assigned to | Task #
Develop Statement of Need | 1 day | Person assigned to | Task #
Market Research | 1 day | Person assigned to | Task #
Statement of Work
Draft SOW | 1 day | Person assigned to | Task #
Review | 1 day | Person assigned to | Task #
SOW Approval | 1 day | Person assigned to | Task #
Acquisition Plan
Draft Acquisition Plan | 1 day | Person assigned to | Task #
Legal Review | 1 day | Person assigned to | Task #
Incorporate Legal Input | 1 day | Person assigned to | Task #
Acquisition Plan Approval | 1 day | Person assigned to | Task #
Source Selection Plan
Draft SSP | 1 day | Person assigned to | Task #
Review | 1 day | Person assigned to | Task #
Incorporate Comments | 1 day | Person assigned to | Task #
SSP Approval | 1 day | Person assigned to | Task #
Final Review of Acquisition Package | 1 day | Person assigned to | Task #
Announcement (Notification of Intent to Solicit) |  | Person assigned to
Develop Announcement | 1 day | Person assigned to | Task #
Review Draft Announcement | 1 day | Person assigned to | Task #
Incorporate comments | 1 day | Person assigned to | Task #
Approval of Announcement | 1 day | Person assigned to | Task #
Announcement Posting | 1 day | Person assigned to | Task #
Receive Questions | 1 day | Person assigned to | Task #
Response to Questions | 1 day | Person assigned to
Issue RFP
Develop RFP | 1 day | Person assigned to | Task #
Review | 1 day | Person assigned to | Task #
Incorporate Comments | 1 day | Person assigned to | Task #
Legal Review of RFP | 1 day | Person assigned to | Task #
Incorporate Legal Comments | 1 day | Person assigned to | Task #
Draft RFP Release | 1 day | Person assigned to | Task #
Approval of Annoucement | 1 day | Person assigned to | Task #
Publish RFP | 1 day | Person assigned to | Task #
Vendor Proposal Preparation |  | Person assigned to
Q&As
Vendor Question Prep & Submission | 1 day | Person assigned to | Task #
Prepare Response to Questions | 1 day | Person assigned to | Task #
Legal Review of Q&As | 1 day | Person assigned to | Task #
Incorporate Changes from Legal | 1 day | Person assigned to | Task #
Release Q&A | 1 day | Person assigned to | Task #
Vendor Response to Q&A and Amend | 1 day | Person assigned to | Task #
Source Selection Preparation |  | Person assigned to
Develop Evaluation Workbook | 1 day | Person assigned to
Identify Evaluation Facility | 1 day | Person assigned to
Coordinate Facility Agreement | 1 day | Person assigned to
Coordination
ID Participants | 1 day | Person assigned to
Prepare Nomination Letter | 1 day | Person assigned to
Sign Nomination Letter | 1 day | Person assigned to
Send Nomination Letter | 1 day | Person assigned to
Final Coordination of Nominees | 1 day | Person assigned to
Schedule Legal Brief | 1 day | Person assigned to
Legal Brief to Participants | 1 day | Person assigned to
Proposal Receipt | 1 day | Person assigned to
Source Selection |  | Person assigned to
Receive, Log, & Validate Proposals | 1 day | Person assigned to
Review Technical Proposals
Review and Score Proposals | 1 day | Person assigned to
Conduct Reconciliation Session | 1 day | Person assigned to
Legal review of workbooks | 1 day | Person assigned to
Review Cost/Price Proposals
Clarifications |  | Person assigned to
Prepare Clarification Letters | 1 day | Person assigned to
Contractor Clarification Preparation | 1 day | Person assigned to
Evaluate Contractor Responses | 1 day | Person assigned to
Present Findings | 1 day | Person assigned to
Competitive Range
Determine Competitive Range | 1 day | Person assigned to
Prepare Competitive Range Memo | 1 day | Person assigned to
Review Competitive Range Memo | 1 day | Person assigned to
Present Competitive Range | 1 day | Person assigned to
Presentations |  | Person assigned to
Schedule Presentations | 1 day | Person assigned to
Conduct Presentations | 1 day | Person assigned to
Evaluate Impact on Scores | 1 day | Person assigned to
Present Findings | 1 day | Person assigned to
Negotiations | 1 day | Person assigned to
Cost/ Tech Tradeoff Analysis | 1 day | Person assigned to
Prepare Decision Memo | 1 day | Person assigned to
Review Decision Memo | 1 day | Person assigned to
Sign Decision Memo | 1 day | Person assigned to
Contract Award | 1 day | Person assigned to